## DB Defects
Dashboard Software Defects | [8 empty] | from | 2009-07-06 | to | 2009-07-12 | 28
Defects week by type and severity
| Cosmetical | Minor | Major | Critical | Total
assigned | 3 | 14 | 23 | 3 | 43 | [6 empty] | Defect assigned fix pending
resolved | 0 | 7 | 9 | 0 | 16 | [6 empty] | Defect assigned, fix delivered, not yet retested
closed | 9 | 79 | 92 | 16 | 196 | [6 empty] | Defect assigned, fix delivered and successfully retested
Total | 12 | 100 | 124 | 19 | 255
Assigned, resolved and concluded defects cumulated over the last 18 weeks | [7 empty] | New defects assigned, resolved and concluded last 18 weeks - week on week
Average resolution / conclusion times in calendar days | [7 empty] | Average resolution / conclusion times in calendar days last 18 weeks
|  |  | Cosmetical | Minor | Major | Critical | Total
Assigned to resolved |  |  | 10.7778 | 20.8721 | 17.5446 | 8.75 | 17.9434
Resolved to closed |  |  | 6.6667 | 13.9241 | 13.2826 | 6.3125 | 12.6684
Assigned to closed |  |  | 17.4444 | 31.7215 | 31.4022 | 15.0625 | 29.5561

## DB Test
Dashboard Software Test Coverage | [10 empty] | 2009-07-10 | 28
Test cases (TCs) by software modules
| # TCs planned total | # TCs planned for end of week | # TCs executed |  |  |  |  | Success rate in % (passed TCs as percentage of finished TCs) Goal: 87% or higher success rate |  | Completion rate | Actual in % of plan (finished TCs as percentage of planned TCs)
|  |  | started | not yet finished | finished | thereof passed | thereof failed |  |  | (finished in % of total plan)
Software Module 1 | 400 | 204 | 209 | 17 | 192 | 170 | 22 |  | 88.54% | 48% |  | 94.12%
Software Module 2 | 300 | 150 | 153 | 9 | 144 | 126 | 18 |  | 87.5% | 48% |  | 96%
Software Module 3 | 600 | 300 | 298 | 22 | 276 | 254 | 22 |  | 92.03% | 46% |  | 92%
Software Module 4 | 800 | 402 | 417 | 4 | 413 | 364 | 49 |  | 88.14% | 51.62% |  | 102.7%
Software Module 5 | 400 | 204 | 204 | 15 | 189 | 164 | 25 |  | 86.77% | 47.25% |  | 92.65%
Total | 2500 | 1260 | 1281 | 67 | 1214 | 1078 | 136 |  | 88.8% | 48.56% |  | 96.35%
Total actual vs plan over time | [7 empty] | Passed test cases and success rate threshold

## DB CRs
Dashboard Software Change Requests | [5 empty] | 2009-07-10 | 28
Overview actual week |  |  |  |  | Change Request development cumulated
Total CRs last week | New this week | Total CRs this week | thereof business | thereof IT
32 | 1 | 33 | 28 | 5
|  |  | 84.85% | 15.15%
Change Requests - actual status
Total |  |  |  | 33
In investigation |  |  |  | 0
Approved (in implementation) |  |  |  | 3
Included (delivered) |  |  |  | 21
Future CRs |  |  |  | 4
Rejected or cancelled |  |  |  | 5
Total Change Requests by department |  |  |  |  | Change Request development cumulated by department

## Data Defects
Data Defects
Defect ID | Severity | State | Assigned on | Resolved on | Concluded on
1 | Critical | closed | 2009-01-28 | 2009-01-28 | 2009-01-30
2 | Major | closed | 2009-01-29 | 2009-01-30 | 2009-01-31
3 | Major | closed | 2009-01-30 | 2009-02-12 | 2009-02-14
4 | Minor | closed | 2009-01-30 | 2009-02-14 | 2009-02-17
5 | Major | closed | 2009-01-30 | 2009-03-17 | 2009-04-01
6 | Minor | closed | 2009-01-31 | 2009-02-10 | 2009-02-11
7 | Minor | closed | 2009-01-31 | 2009-02-04 | 2009-03-27
8 | Minor | closed | 2009-02-03 | 2009-02-14 | 2009-07-14
9 | Minor | closed | 2009-02-06 | 2009-02-13 | 2009-02-17
10 | Minor | closed | 2009-02-07 | 2009-02-14 | 2009-03-06
11 | Major | closed | 2009-02-07 | 2009-02-28 | 2009-03-04
12 | Minor | closed | 2009-02-07 | 2009-03-05 | 2009-03-07
13 | Minor | closed | 2009-02-08 | 2009-02-13 | 2009-02-25
14 | Minor | closed | 2009-02-08 | 2009-02-28 | 2009-03-07
15 | Cosmetical | closed | 2009-02-10 | 2009-03-13 | 2009-03-14
16 | Major | closed | 2009-02-11 | 2009-02-28 | 2009-04-01
17 | Minor | closed | 2009-02-11 | 2009-02-13 | 2009-06-13
18 | Minor | closed | 2009-02-12 | 2009-02-13 | 2009-09-15
19 | Major | closed | 2009-02-12 | 2009-02-12 | 2009-07-08
20 | Cosmetical | closed | 2009-02-13 | 2009-02-18 | 2009-02-19
21 | Major | closed | 2009-02-13 | 2009-02-28 | 2009-03-03
22 | Major | closed | 2009-02-13 | 2009-02-20 | 2009-02-25
23 | Major | closed | 2009-02-13 | 2009-02-28 | 2009-03-05
24 | Major | closed | 2009-02-13 | 2009-02-14 | 2009-02-14
25 | Minor | closed | 2009-02-15 | 2009-04-07 | 2009-05-09
26 | Minor | closed | 2009-02-15 | 2009-04-07 | 2009-04-10
27 | Major | closed | 2009-02-17 | 2009-03-04 | 2009-03-07
28 | Minor | closed | 2009-02-18 | 2009-02-18 | 2009-02-19
29 | Minor | closed | 2009-02-19 | 2009-04-07 | 2009-04-12
30 | Minor | closed | 2009-02-19 | 2009-04-07 | 2009-06-30
31 | Major | closed | 2009-02-19 | 2009-04-07 | 2009-04-12
32 | Major | closed | 2009-02-19 | 2009-04-18 | 2009-04-18
33 | Cosmetical | closed | 2009-02-19 | 2009-02-20 | 2009-03-27
34 | Major | closed | 2009-02-19 | 2009-03-13 | 2009-03-20
35 | Minor | closed | 2009-02-19 | 2009-03-13 | 2009-04-17
36 | Major | closed | 2009-02-20 | 2009-03-13 | 2009-03-25
37 | Major | closed | 2009-02-20 | 2009-03-13 | 2009-05-05
38 | Major | closed | 2009-02-20 | 2009-04-14 | 2009-04-14
39 | Major | closed | 2009-02-21 | 2009-02-24 | 2009-02-24
40 | Major | closed | 2009-02-21 | 2009-04-03 | 2009-05-05
41 | Minor | closed | 2009-02-25 | 2009-03-13 | 2009-05-06
42 | Major | closed | 2009-02-25 | 2009-04-02 | 2009-04-16
43 | Minor | closed | 2009-02-25 | 2009-03-20 | 2009-03-27
44 | Major | closed | 2009-02-26 | 2009-03-13 | 2009-04-24
45 | Major | closed | 2009-02-26 | 2009-03-18 | 2009-04-01
46 | Minor | closed | 2009-02-26 | 2009-08-17 | 2009-09-18
47 | Major | closed | 2009-02-26 | 2009-02-26 | 2009-02-26
48 | Major | closed | 2009-02-27 | 2009-04-08 | 2009-05-01
49 | Minor | closed | 2009-02-27 | 2009-04-07 | 2009-04-22
50 | Major | closed | 2009-02-27 | 2009-03-24 | 2009-04-10
51 | Minor | closed | 2009-02-28 | 2009-03-07 | 2009-05-02
52 | Minor | closed | 2009-02-28 | 2009-03-13 | 2009-03-25
53 | Minor | closed | 2009-03-01 | 2009-03-13 | 2009-03-14
54 | Major | closed | 2009-03-05 | 2009-04-07 | 2009-06-13
55 | Minor | closed | 2009-03-05 | 2009-03-20 | 2009-03-21
56 | Major | closed | 2009-03-05 | 2009-04-07 | 2009-06-13
57 | Major | closed | 2009-03-05 | 2009-04-07 | 2009-06-13
58 | Minor | closed | 2009-03-05 | 2009-04-07 | 2009-06-13
59 | Minor | closed | 2009-03-05 | 2009-04-07 | 2009-06-13
60 | Major | closed | 2009-03-05 | 2009-03-05 | 2009-03-05
61 | Major | closed | 2009-03-05 | 2009-04-07 | 2009-04-10
62 | Minor | closed | 2009-03-05 | 2009-04-07 | 2009-04-10
63 | Minor | closed | 2009-03-06 | 2009-03-07 | 2009-03-07
64 | Minor | closed | 2009-03-06 | 2009-03-13 | 2009-03-25
65 | Minor | closed | 2009-03-06 | 2009-04-22 | 2009-04-29
66 | Major | closed | 2009-03-07 | 2009-04-03 | 2009-06-10
67 | Minor | closed | 2009-03-08 | 2009-07-10 | 2009-07-14
68 | Cosmetical | closed | 2009-03-10 | 2009-03-13 | 2009-03-14
69 | Cosmetical | closed | 2009-03-10 | 2009-03-13 | 2009-03-14
70 | Cosmetical | closed | 2009-03-10 | 2009-03-13 | 2009-03-14
71 | Minor | closed | 2009-03-11 | 2009-03-21 | 2009-03-25
72 | Major | closed | 2009-03-11 | 2009-04-02 | 2009-04-15
73 | Major | closed | 2009-03-11 | 2009-04-07 | 2009-04-24
74 | Major | closed | 2009-03-11 | 2009-04-07 | 2009-04-18
75 | Minor | closed | 2009-03-11 | 2009-03-18 | 2009-03-25
76 | Major | closed | 2009-03-11 | 2009-04-07 | 2009-05-01
77 | Major | closed | 2009-03-12 | 2009-03-17 | 2009-04-03
78 | Major | closed | 2009-03-13 | 2009-03-25 | 2009-03-25
79 | Major | closed | 2009-03-14 | 2009-04-02 | 2009-04-09
80 | Minor | closed | 2009-03-14 | 2009-07-10 | 2009-07-18
81 | Minor | closed | 2009-03-15 | 2009-03-16 | 2009-03-23
82 | Minor | closed | 2009-03-15 | 2009-03-16 | 2009-03-23
83 | Major | closed | 2009-03-15 | 2009-04-02 | 2009-04-30
84 | Critical | closed | 2009-03-15 | 2009-04-02 | 2009-04-24
85 | Major | closed | 2009-03-15 | 2009-04-22 | 2009-04-24
86 | Minor | closed | 2009-03-15 | 2009-04-08 | 2009-04-09
87 | Major | closed | 2009-03-18 | 2009-03-18 | 2009-03-18
88 | Minor | closed | 2009-03-18 | 2009-04-07 | 2009-06-13
89 | Major | closed | 2009-03-20 | 2009-04-02 | 2009-05-05
90 | Minor | closed | 2009-03-20 | 2009-04-03 | 2009-04-14
91 | Minor | closed | 2009-03-21 | 2009-04-03 | 2009-04-08
92 | Minor | closed | 2009-03-24 | 2009-04-07 | 2009-06-13
93 | Major | closed | 2009-03-25 | 2009-04-02 | 2009-04-08
94 | Critical | closed | 2009-03-25 | 2009-04-02 | 2009-04-16
95 | Major | closed | 2009-03-25 | 2009-04-03 | 2009-04-04
96 | Minor | closed | 2009-03-25 | 2009-04-02 | 2009-04-03
97 | Minor | closed | 2009-03-25 | 2009-04-18 | 2009-05-05
98 | Major | closed | 2009-03-27 | 2009-05-22 | 2009-05-23
99 | Major | closed | 2009-03-27 | 2009-04-02 | 2009-04-03
100 | Major | closed | 2009-03-27 | 2009-04-03 | 2009-04-17
101 | Minor | closed | 2009-03-28 | 2009-04-18 | 2009-04-22
102 | Major | closed | 2009-03-28 | 2009-04-08 | 2009-05-08
103 | Minor | closed | 2009-03-31 | 2009-04-07 | 2009-04-10
104 | Cosmetical | closed | 2009-04-01 | 2009-04-09 | 2009-04-23
105 | Critical | closed | 2009-04-03 | 2009-04-08 | 2009-04-09
106 | Minor | closed | 2009-04-05 | 2009-04-16 | 2009-04-17
107 | Major | closed | 2009-04-05 | 2009-04-24 | 2009-04-30
108 | Minor | closed | 2009-04-08 | 2009-05-12 | 2009-05-22
109 | Major | closed | 2009-04-08 | 2009-04-18 | 2009-04-22
110 | Minor | closed | 2009-04-08 | 2009-04-18 | 2009-04-22
111 | Major | closed | 2009-04-09 | 2009-07-15 | 2009-07-22
112 | Minor | closed | 2009-04-09 | 2009-04-18 | 2009-04-23
113 | Minor | closed | 2009-04-09 | 2009-04-18 | 2009-04-23
114 | Minor | closed | 2009-04-09 | 2009-04-16 | 2009-04-17
115 | Minor | closed | 2009-04-09 | 2009-05-22 | 2009-05-22
116 | Major | closed | 2009-04-10 | 2009-07-15 | 2009-08-18
117 | Major | closed | 2009-04-10 | 2009-04-10 | 2009-04-10
118 | Minor | closed | 2009-04-10 | 2009-05-15 | 2009-05-23
119 | Critical | closed | 2009-04-11 | 2009-04-18 | 2009-04-23
120 | Minor | closed | 2009-04-11 | 2009-05-01 | 2009-05-02
121 | Minor | closed | 2009-04-14 | 2009-05-22 | 2009-06-10
122 | Major | closed | 2009-04-14 | 2009-04-15 | 2009-04-24
123 | Major | closed | 2009-04-16 | 2009-04-22 | 2009-04-24
124 | Major | closed | 2009-04-16 | 2009-05-29 | 2009-05-30
125 | Critical | closed | 2009-04-16 | 2009-05-09 | 2009-05-14
126 | Minor | closed | 2009-04-16 | 2009-05-09 | 2009-05-13
127 | Major | closed | 2009-04-17 | 2009-05-01 | 2009-09-19
128 | Major | closed | 2009-04-17 | 2009-05-01 | 2009-05-07
129 | Minor | closed | 2009-04-17 | 2009-07-22 | 2009-09-19
130 | Major | closed | 2009-04-17 | 2009-05-09 | 2009-05-09
131 | Minor | closed | 2009-04-17 | 2009-05-05 | 2009-05-06
132 | Major | closed | 2009-04-17 | 2009-05-01 | 2009-05-06
133 | Critical | closed | 2009-04-18 | 2009-05-22 | 2009-05-29
134 | Major | closed | 2009-04-22 | 2009-05-23 | 2009-06-02
135 | Major | closed | 2009-04-22 | 2009-05-23 | 2009-06-03
136 | Major | closed | 2009-04-22 | 2009-05-11 | 2009-05-13
137 | Major | closed | 2009-04-23 | 2009-05-23 | 2009-05-23
138 | Major | closed | 2009-04-23 | 2009-07-15 | 2009-07-22
139 | Major | closed | 2009-04-23 | 2009-05-22 | 2009-05-31
140 | Cosmetical | closed | 2009-04-24 | 2009-07-22 | 2009-07-30
141 | Minor | closed | 2009-04-25 | 2009-05-01 | 2009-05-01
142 | Minor | closed | 2009-04-29 | 2009-04-29 | 2009-04-29
143 | Minor | closed | 2009-04-30 | 2009-07-10 | 2009-07-10
144 | Minor | closed | 2009-04-30 | 2009-07-03 | 2009-07-19
145 | Minor | closed | 2009-04-30 | 2009-05-23 | 2009-05-23
146 | Minor | closed | 2009-04-30 | 2009-05-12 | 2009-06-03
147 | Major | closed | 2009-04-30 | 2009-05-22 | 2009-05-28
148 | Major | resolved | 2009-05-01 | 2009-05-22 | 2009-05-30
149 | Major | closed | 2009-05-01 | 2009-05-29 | 2009-06-09
150 | Minor | closed | 2009-05-01 | 2009-05-12 | 2009-06-06
151 | Major | closed | 2009-05-01 | 2009-05-22 | 2009-05-23
152 | Major | closed | 2009-05-02 | 2009-05-29 | 2009-05-30
153 | Major | closed | 2009-05-02 | 2009-05-21 | 2009-05-23
154 | Critical | closed | 2009-05-02 | 2009-05-06 | 2009-05-06
155 | Minor | closed | 2009-05-02 | 2009-05-29 | 2009-06-10
156 | Minor | closed | 2009-05-03 | 2009-05-12 | 2009-05-23
157 | Minor | closed | 2009-05-03 | 2009-05-09 | 2009-05-21
158 | Major | closed | 2009-05-03 | 2009-05-29 | 2009-07-01
159 | Major | closed | 2009-05-06 | 2009-05-22 | 2009-05-29
160 | Major | closed | 2009-05-06 | 2009-05-22 | 2009-05-23
161 | Major | closed | 2009-05-06 | 2009-05-23 | 2009-05-23
162 | Minor | closed | 2009-05-06 | 2009-07-10 | 2009-07-19
163 | Critical | closed | 2009-05-06 | 2009-05-09 | 2009-05-09
164 | Major | closed | 2009-05-07 | 2009-06-04 | 2009-06-10
165 | Minor | closed | 2009-05-07 | 2009-05-22 | 2009-06-02
166 | Major | closed | 2009-05-08 | 2009-05-22 | 2009-05-29
167 | Minor | closed | 2009-05-08 | 2009-07-24 | 2009-07-25
168 | Major | closed | 2009-05-08 | 2009-07-15 | 2009-07-22
169 | Critical | closed | 2009-05-09 | 2009-05-15 | 2009-05-22
170 | Critical | closed | 2009-05-09 | 2009-07-31 | 2009-08-12
171 | Cosmetical | closed | 2009-05-12 | 2009-05-29 | 2009-06-03
172 | Major | closed | 2009-05-13 | 2009-05-19 | 2009-05-21
173 | Minor | closed | 2009-05-14 | 2009-07-15 | 2009-10-01
174 | Cosmetical | closed | 2009-05-15 | 2009-06-10 | 2009-06-11
175 | Minor | closed | 2009-05-16 | 2009-06-29 | 2009-07-08
176 | Major | closed | 2009-05-19 | 2009-05-28 | 2009-07-30
177 | Major | closed | 2009-05-19 | 2009-05-22 | 2009-07-11
178 | Critical | closed | 2009-05-21 | 2009-07-15 | 2009-07-25
179 | Minor | closed | 2009-05-22 | 2009-06-04 | 2009-06-04
180 | Minor | closed | 2009-05-22 | 2009-07-15 | 2009-08-18
181 | Critical | closed | 2009-05-23 | 2009-05-29 | 2009-06-02
182 | Critical | closed | 2009-05-23 | 2009-05-29 | 2009-05-30
183 | Minor | closed | 2009-05-23 | 2009-05-30 | 2009-05-30
184 | Minor | closed | 2009-05-24 | 2009-09-01 | 2009-09-30
185 | Critical | closed | 2009-05-24 | 2009-05-30 | 2009-06-03
186 | Critical | closed | 2009-05-26 | 2009-05-27 | 2009-05-28
187 | Major | closed | 2009-05-26 | 2009-07-15 | 2009-07-22
188 | Major | closed | 2009-05-27 | 2009-06-04 | 2009-06-09
189 | Major | closed | 2009-05-27 | 2009-07-15 | 2009-07-22
190 | Minor | closed | 2009-05-27 | 2009-06-07 | 2009-07-08
191 | Critical | closed | 2009-05-28 | 2009-07-15 | 2009-07-23
192 | Major | closed | 2009-05-28 | 2009-05-30 | 2009-06-03
193 | Major | closed | 2009-05-28 | 2009-06-04 | 2009-06-10
194 | Major | closed | 2009-05-28 | 2009-06-10 | 2009-06-10
195 | Minor | closed | 2009-05-29 | 2009-10-21 | 2009-10-21
196 | Major | closed | 2009-05-29 | 2009-06-05 | 2009-06-06
197 | Major | closed | 2009-05-30 | 2009-07-22 | 2009-07-30
198 | Minor | closed | 2009-05-30 | 2009-05-31 | 2009-06-06
199 | Critical | closed | 2009-05-31 | 2009-06-10 | 2009-07-08
200 | Major | closed | 2009-06-02 | 2009-06-10 | 2009-06-13
201 | Major | closed | 2009-06-02 | 2009-06-07 | 2009-06-09
202 | Major | closed | 2009-06-02 | 2009-07-31 | 2009-09-12
203 | Minor | closed | 2009-06-03 | 2009-06-10 | 2009-06-10
204 | Minor | closed | 2009-06-03 | 2009-06-30 | 2009-07-10
205 | Minor | closed | 2009-06-03 | 2009-06-13 | 2009-06-13
206 | Major | closed | 2009-06-03 | 2009-06-04 | 2009-07-07
207 | Major | closed | 2009-06-03 | 2009-07-15 | 2009-07-28
208 | Minor | closed | 2009-06-03 | 2009-06-29 | 2009-07-01
209 | Minor | closed | 2009-06-03 | 2009-06-10 | 2009-06-11
210 | Minor | closed | 2009-06-03 | 2009-06-10 | 2009-06-11
211 | Minor | closed | 2009-06-04 | 2009-07-15 | 2009-08-18
212 | Major | closed | 2009-06-04 | 2009-06-04 | 2009-06-11
213 | Major | closed | 2009-06-04 | 2009-06-25 | 2009-07-03
214 | Minor | closed | 2009-06-04 | 2009-06-30 | 2009-06-30
215 | Major | closed | 2009-06-05 | 2009-06-10 | 2009-06-10
216 | Minor | closed | 2009-06-05 | 2009-07-22 | 2009-07-22
217 | Major | closed | 2009-06-09 | 2009-06-11 | 2009-06-11
218 | Major | closed | 2009-06-09 | 2009-07-15 | 2009-07-28
219 | Major | closed | 2009-06-10 | 2009-06-25 | 2009-07-04
220 | Major | closed | 2009-06-11 | 2009-06-19 | 2009-07-04
221 | Major | closed | 2009-06-11 | 2009-06-14 | 2009-07-25
222 | Major | closed | 2009-06-11 | 2009-06-25 | 2009-07-09
223 | Major | closed | 2009-06-11 | 2009-07-10 | 2009-07-16
224 | Major | closed | 2009-06-12 | 2009-07-03 | 2009-07-24
225 | Minor | closed | 2009-06-12 | 2009-07-21 | 2009-07-28
226 | Major | resolved | 2009-06-13 | 2009-07-23 | 2009-07-29
227 | Major | closed | 2009-06-18 | 2009-07-15 | 2009-07-28
228 | Major | closed | 2009-06-23 | 2009-07-03 | 2009-07-15
229 | Major | closed | 2009-06-23 | 2009-07-10 | 2009-07-16
230 | Minor | closed | 2009-06-23 | 2009-07-07 | 2009-07-08
231 | Major | closed | 2009-06-24 | 2009-07-15 | 2009-07-28
232 | Major | closed | 2009-06-24 | 2009-07-15 | 2009-07-25
233 | Major | closed | 2009-06-25 | 2009-07-24 | 2009-07-25
234 | Minor | closed | 2009-06-25 | 2009-07-03 | 2009-07-05
235 | Major | closed | 2009-06-25 | 2009-07-15 | 2009-07-24
236 | Major | closed | 2009-06-28 | 2009-06-29 | 2009-07-02
237 | Critical | closed | 2009-06-30 | 2009-07-03 | 2009-07-03
238 | Major | closed | 2009-07-02 | 2009-07-03 | 2009-07-18
239 | Major | closed | 2009-07-02 | 2009-07-03 | 2009-07-15
240 | Minor | closed | 2009-07-02 | 2009-07-03 | 2009-07-03
241 | Major | closed | 2009-07-03 | 2009-07-22 | 2009-07-25
242 | Minor | closed | 2009-07-03 | 2009-07-21 | 2009-07-28
243 | Major | closed | 2009-07-03 | 2009-07-18 | 2009-07-21
244 | Major | closed | 2009-07-04 | 2009-07-21 | 2009-08-04
245 | Minor | closed | 2009-07-04 | 2009-07-10 | 2009-07-15
246 | Minor | closed | 2009-07-07 | 2009-07-10 | 2009-07-12
247 | Cosmetical | closed | 2009-07-07 | 2009-07-21 | 2009-08-07
248 | Major | closed | 2009-07-07 | 2009-07-18 | 2009-07-24
249 | Minor | closed | 2009-07-07 | 2009-07-21 | 2009-08-12
250 | Minor | closed | 2009-07-07 | 2009-07-22 | 2009-07-25
251 | Major | closed | 2009-07-07 | 2009-07-18 | 2009-07-30
252 | Minor | closed | 2009-07-07 | 2009-07-21 | 2009-07-24
253 | Cosmetical | closed | 2009-07-09 | 2009-07-24 | 2009-08-07
254 | Major | closed | 2009-07-09 | 2009-07-18 | 2009-07-25
255 | Major | closed | 2009-07-10 | 2009-07-18 | 2009-07-28
256 | Major | closed | 2009-07-15 | 2009-07-31 | 2009-09-17
257 | Minor | closed | 2009-07-15 | 2009-08-07 | 2009-08-08
258 | Minor | closed | 2009-07-16 | 2009-08-15 | 2009-08-21
259 | Major | closed | 2009-07-16 | 2009-08-15 | 2009-09-03
260 | Major | closed | 2009-07-21 | 2009-07-31 | 2009-07-31
261 | Major | closed | 2009-07-21 | 2009-07-28 | 2009-08-13
262 | Minor | closed | 2009-07-22 | 2009-09-02 | 2009-09-20
263 | Major | closed | 2009-07-22 | 2009-08-07 | 2009-09-01
264 | Minor | closed | 2009-07-23 | 2009-08-05 | 2009-09-04
265 | Major | resolved | 2009-07-23 | 2009-09-02 | 2009-09-10
266 | Major | resolved | 2009-07-23 | 2009-09-02 | 2009-09-09
267 | Minor | closed | 2009-07-23 | 2009-07-29 | 2009-07-30
268 | Major | closed | 2009-07-23 | 2009-07-29 | 2009-07-31
269 | Cosmetical | closed | 2009-07-24 | 2009-08-05 | 2009-08-08
270 | Minor | closed | 2009-07-25 | 2009-08-05 | 2009-08-12
271 | Minor | closed | 2009-07-25 | 2009-09-03 | 2009-09-11
272 | Minor | closed | 2009-07-25 | 2009-08-05 | 2009-09-11
273 | Major | closed | 2009-07-29 | 2009-08-15 | 2009-08-25
274 | Minor | closed | 2009-07-29 | 2009-09-02 | 2009-09-24
275 | Minor | closed | 2009-07-30 | 2009-07-30 | 2009-07-30
276 | Major | closed | 2009-07-30 | 2009-08-06 | 2009-09-16
277 | Major | closed | 2009-08-01 | 2009-08-21 | 2009-09-08
278 | Cosmetical | closed | 2009-08-01 | 2009-08-07 | 2009-08-11
279 | Critical | closed | 2009-08-01 | 2009-08-06 | 2009-08-13
280 | Major | closed | 2009-08-05 | 2009-09-12 | 2009-09-29
281 | Major | closed | 2009-08-05 | 2009-08-15 | 2009-08-25
282 | Major | closed | 2009-08-05 | 2009-09-01 | 2009-10-02
283 | Major | closed | 2009-08-06 | 2009-10-08 | 2009-10-17
284 | Major | closed | 2009-08-08 | 2009-08-17 | 2009-08-26
285 | Major | closed | 2009-08-08 | 2009-08-11 | 2009-08-26
286 | Minor | closed | 2009-08-08 | 2009-09-08 | 2009-10-02
287 | Critical | closed | 2009-08-11 | 2009-08-13 | 2009-09-03
288 | Minor | closed | 2009-08-12 | 2009-08-18 | 2009-09-08
289 | Major | closed | 2009-08-14 | 2009-09-30 | 2009-10-02
290 | Major | closed | 2009-08-15 | 2009-08-19 | 2009-08-26
291 | Critical | closed | 2009-08-15 | 2009-08-16 | 2009-08-18
292 | Major | closed | 2009-08-18 | 2009-10-07 | 2009-10-09
293 | Major | closed | 2009-08-18 | 2009-10-08 | 2009-10-17
294 | Major | closed | 2009-08-18 | 2009-09-05 | 2009-09-22
295 | Major | closed | 2009-08-19 | 2009-09-26 | 2009-09-29
296 | Minor | closed | 2009-08-19 | 2009-09-06 | 2009-09-22
297 | Minor | closed | 2009-08-21 | 2009-09-02 | 2009-09-10
298 | Major | closed | 2009-08-22 | 2009-10-14 | 2009-10-21
299 | Major | closed | 2009-08-22 | 2009-09-06 | 2009-09-23
300 | Major | closed | 2009-08-26 | 2009-08-27 | 2009-08-27
301 | Minor | closed | 2009-08-26 | 2009-08-28 | 2009-09-04
302 | Minor | closed | 2009-08-26 | 2009-09-11 | 2009-10-01
303 | Major | closed | 2009-08-26 | 2009-09-01 | 2009-09-04
304 | Major | assigned | 2009-08-26 | 2009-09-03 | 2009-09-09
305 | Cosmetical | resolved | 2009-08-29 | 2009-10-14 | 2009-10-21
306 | Major | closed | 2009-08-29 | 2009-09-05 | 2009-10-02
307 | Major | closed | 2009-09-01 | 2009-10-14 | 2009-10-21
308 | Minor | closed | 2009-09-03 | 2009-10-14 | 2009-10-20
309 | Cosmetical | assigned | 2009-09-03 | 2009-09-15 | 2009-09-21
310 | Minor | closed | 2009-09-05 | 2009-09-26 | 2009-09-27
311 | Major | closed | 2009-09-05 | 2009-09-18 | 2009-09-23
312 | Minor | assigned | 2009-09-06 | 2009-09-14 | 2009-09-23
313 | Minor | closed | 2009-09-08 | 2009-09-11 | 2009-09-23
314 | Minor | closed | 2009-09-08 | 2009-09-11 | 2009-09-11
315 | Minor | closed | 2009-09-08 | 2009-09-18 | 2009-09-24
316 | Major | resolved | 2009-09-08 | 2009-10-14 | 2009-10-21
317 | Major | closed | 2009-09-09 | 2009-09-22 | 2009-09-30
318 | Cosmetical | closed | 2009-09-09 | 2009-09-16 | 2009-09-26
319 | Major | closed | 2009-09-10 | 2009-09-18 | 2009-09-19
320 | Major | closed | 2009-09-10 | 2009-09-18 | 2009-09-19
321 | Minor | closed | 2009-09-10 | 2009-09-23 | 2009-09-24
322 | Major | closed | 2009-09-10 | 2009-09-23 | 2009-10-02
323 | Major | closed | 2009-09-11 | 2009-09-20 | 2009-09-29
324 | Minor | closed | 2009-09-11 | 2009-09-18 | 2009-09-24
325 | Minor | closed | 2009-09-11 | 2009-09-20 | 2009-10-03
326 | Minor | closed | 2009-09-11 | 2009-09-11 | 2009-10-01
327 | Minor | closed | 2009-09-11 | 2009-09-18 | 2009-09-29
328 | Major | closed | 2009-09-12 | 2009-09-23 | 2009-10-01
329 | Major | closed | 2009-09-13 | 2009-09-21 | 2009-10-01
330 | Major | assigned | 2009-09-13 | 2009-09-23 | 2009-09-30
331 | Cosmetical | closed | 2009-09-13 | 2009-09-22 | 2009-09-26
332 | Cosmetical | closed | 2009-09-15 | 2009-09-25 | 2009-09-29
333 | Minor | closed | 2009-09-16 | 2009-09-30 | 2009-10-03
334 | Major | closed | 2009-09-16 | 2009-09-26 | 2009-09-30
335 | Minor | closed | 2009-09-16 | 2009-09-23 | 2009-09-25
336 | Minor | resolved | 2009-09-16 | 2009-10-14 | 2009-10-23
337 | Major | resolved | 2009-09-16 | 2009-10-14 | 2009-10-20
338 | Major | closed | 2009-09-17 | 2009-09-26 | 2009-09-30
339 | Major | closed | 2009-09-17 | 2009-09-23 | 2009-09-23
340 | Major | closed | 2009-09-18 | 2009-10-14 | 2009-10-17
341 | Minor | closed | 2009-09-18 | 2009-09-25 | 2009-09-26
342 | Minor | assigned | 2009-09-19 | 2009-09-29 | 2009-10-05
343 | Minor | closed | 2009-09-19 | 2009-09-26 | 2009-10-02
344 | Major | resolved | 2009-09-19 | 2009-10-14 | 2009-10-23
345 | Minor | resolved | 2009-09-19 | 2009-10-14 | 2009-10-19
346 | Major | closed | 2009-09-20 | 2009-09-26 | 2009-09-27
347 | Minor | closed | 2009-09-22 | 2009-09-25 | 2009-10-03
348 | Minor | closed | 2009-09-23 | 2009-09-26 | 2009-09-30
349 | Minor | closed | 2009-09-24 | 2009-09-24 | 2009-09-24
350 | Major | closed | 2009-09-25 | 2009-09-30 | 2009-10-03
351 | Cosmetical | closed | 2009-09-25 | 2009-09-26 | 2009-09-29
352 | Major | resolved | 2009-09-25 | 2009-10-14 | 2009-10-22
353 | Major | resolved | 2009-09-25 | 2009-10-14 | 2009-10-19
354 | Minor | closed | 2009-09-26 | 2009-10-15 | 2009-10-20
355 | Major | resolved | 2009-09-26 | 2009-10-14 | 2009-10-19
356 | Major | closed | 2009-09-29 | 2009-10-14 | 2009-10-28
357 | Major | closed | 2009-09-30 | 2009-10-14 | 2009-10-17
358 | Minor | resolved | 2009-09-30 | 2009-10-14 | 2009-10-20
359 | Minor | closed | 2009-10-01 | 2009-10-14 | 2009-10-17
360 | Cosmetical | closed | 2009-10-02 | 2009-10-21 | 2009-10-22
361 | Major | resolved | 2009-10-02 | 2009-10-23 | 2009-10-29
362 | Major | resolved | 2009-10-02 | 2009-10-23 | 2009-10-29
363 | Minor | resolved | 2009-10-02 | 2009-10-17 | 2009-10-27
364 | Minor | resolved | 2009-10-02 | 2009-10-15 | 2009-10-22
365 | Major | closed | 2009-10-02 | 2009-10-04 | 2009-10-09
366 | Minor | resolved | 2009-10-03 | 2009-10-14 | 2009-10-24
367 | Minor | resolved | 2009-10-03 | 2009-10-14 | 2009-10-21
368 | Minor | resolved | 2009-10-03 | 2009-10-03 | 2009-10-11
369 | Cosmetical | assigned | 2009-10-06 | 2009-10-15 | 2009-10-20
370 | Major | closed | 2009-10-08 | 2009-10-20 | 2009-11-03
371 | Major | resolved | 2009-10-08 | 2009-10-20 | 2009-10-25
372 | Minor | resolved | 2009-10-09 | 2009-10-24 | 2009-11-01
373 | Minor | resolved | 2009-10-09 | 2009-10-20 | 2009-10-30
374 | Major | closed | 2009-10-09 | 2009-10-21 | 2009-10-22
375 | Cosmetical | resolved | 2009-10-13 | 2009-10-24 | 2009-11-01
376 | Minor | resolved | 2009-10-13 | 2009-10-23 | 2009-10-29
377 | Minor | closed | 2009-10-15 | 2009-10-21 | 2009-10-22
378 | Major | assigned | 2009-10-16 | 2009-10-23 | 2009-10-28
379 | Major | assigned | 2009-10-16 | 2009-10-24 | 2009-11-02
380 | Minor | closed | 2009-10-20 | 2009-10-23 | 2009-10-30
381 | Cosmetical | assigned | 2009-10-20 | 2009-10-29 | 2009-11-08
382 | Major | assigned | 2009-10-21 | 2009-11-01 | 2009-11-08
383 | Minor | assigned | 2009-10-21 | 2009-11-01 | 2009-11-10
384 | Major | closed | 2009-10-21 | 2009-10-22 | 2009-10-28
385 | Major | assigned | 2009-10-22 | 2009-11-02 | 2009-11-08
386 | Minor | assigned | 2009-10-23 | 2009-10-30 | 2009-11-04
387 | Minor | assigned | 2009-10-23 | 2009-10-30 | 2009-11-09
388 | Major | assigned | 2009-10-24 | 2009-10-31 | 2009-11-10
389 | Major | assigned | 2009-10-24 | 2009-09-02 | 2009-09-09
390 | Major | resolved | 2009-10-27 | 2009-11-03 | 2009-11-13
391 | Major | assigned | 2009-10-27 | 2009-11-08 | 2009-11-13
392 | Major | assigned | 2009-10-28 | 2009-11-09 | 2009-11-17
393 | Minor | assigned | 2009-10-28 | 2009-11-08 | 2009-11-18
394 | Minor | resolved | 2009-10-28 | 2009-10-28 | 2009-11-04
395 | Minor | assigned | 2009-10-28 | 2009-11-07 | 2009-11-16
396 | Major | closed | 2009-10-28 | 2009-10-30 | 2009-10-30
397 | Major | assigned | 2009-10-28 | 2009-11-07 | 2009-11-13
398 | Major | assigned | 2009-10-28 | 2009-11-07 | 2009-11-13
399 | Major | assigned | 2009-10-30 | 2009-10-16 | 2009-10-24
400 | Minor | assigned | 2009-10-30 | 2009-11-10 | 2009-11-17
401 | Minor | assigned | 2009-10-30 | 2009-11-09 | 2009-11-18
402 | Minor | assigned | 2009-11-03 | 2009-11-13 | 2009-11-22
403 | Major | assigned | 2009-11-03 | 2009-11-15 | 2009-11-25
404 | Minor | assigned | 2009-11-03 | 2009-11-14 | 2009-11-23
405 | Major | assigned | 2009-11-03 | 2009-11-13 | 2009-11-20
406 | Critical | assigned | 2009-11-03 | 2009-11-14 | 2009-11-22
407 | Minor | assigned | 2009-11-03 | 2009-11-12 | 2009-11-21
408 | Minor | assigned | 2009-11-03 | 2009-11-10 | 2009-11-15
409 | Minor | assigned | 2009-11-03 | 2009-11-11 | 2009-11-18
410 | Minor | assigned | 2009-11-03 | 2009-11-10 | 2009-11-17
411 | Minor | assigned | 2009-11-03 | 2009-11-15 | 2009-11-21
412 | Minor | assigned | 2009-11-03 | 2009-11-11 | 2009-11-17
413 | Major | assigned | 2009-11-03 | 2009-11-13 | 2009-11-21
414 | Minor | assigned | 2009-11-04 | 2009-11-16 | 2009-11-26
415 | Major | assigned | 2009-11-04 | 2009-11-12 | 2009-11-21

## Data Test
Data Test
Planned test cases by module
Software Module 1 |  | 400
Software Module 2 |  | 300
Software Module 3 |  | 600
Software Module 4 |  | 800
Software Module 5 |  | 400
Test threshold success rate |  | 87% | goal of successfully conducted test cases in % of all test cases
Threshold completion rate |  | 95% | highlight if actual completion rate is lower than this threshold
#TCs cumulated
Week | Date | Software Module | #TCs completed | #TCs not completed | #TCs passed | #TCs failed
23 | 2009-06-05 | Software Module 1 | 29 | 1 | 25 | 4
23 | 2009-06-05 | Software Module 2 | 21 | 1 | 19 | 2
23 | 2009-06-05 | Software Module 3 | 49 | 1 | 46 | 3
23 | 2009-06-05 | Software Module 4 | 55 | 2 | 49 | 6
23 | 2009-06-05 | Software Module 5 | 37 | 2 | 30 | 7
24 | 2009-06-12 | Software Module 1 | 67 | 5 | 60 | 7
24 | 2009-06-12 | Software Module 2 | 51 | 2 | 46 | 5
24 | 2009-06-12 | Software Module 3 | 97 | 9 | 92 | 5
24 | 2009-06-12 | Software Module 4 | 132 | 7 | 120 | 12
24 | 2009-06-12 | Software Module 5 | 68 | 1 | 59 | 9
25 | 2009-06-19 | Software Module 1 | 102 | 0 | 93 | 9
25 | 2009-06-19 | Software Module 2 | 71 | 4 | 62 | 9
25 | 2009-06-19 | Software Module 3 | 143 | 13 | 129 | 14
25 | 2009-06-19 | Software Module 4 | 210 | 11 | 180 | 30
25 | 2009-06-19 | Software Module 5 | 98 | 0 | 86 | 12
26 | 2009-06-26 | Software Module 1 | 131 | 12 | 117 | 14
26 | 2009-06-26 | Software Module 2 | 92 | 6 | 80 | 12
26 | 2009-06-26 | Software Module 3 | 189 | 0 | 173 | 16
26 | 2009-06-26 | Software Module 4 | 271 | 24 | 236 | 35
26 | 2009-06-26 | Software Module 5 | 125 | 4 | 104 | 21
27 | 2009-07-03 | Software Module 1 | 158 | 3 | 139 | 19
27 | 2009-07-03 | Software Module 2 | 116 | 0 | 102 | 14
27 | 2009-07-03 | Software Module 3 | 229 | 0 | 212 | 17
27 | 2009-07-03 | Software Module 4 | 342 | 24 | 307 | 35
27 | 2009-07-03 | Software Module 5 | 156 | 8 | 133 | 23
28 | 2009-07-10 | Software Module 1 | 192 | 17 | 170 | 22
28 | 2009-07-10 | Software Module 2 | 144 | 9 | 126 | 18
28 | 2009-07-10 | Software Module 3 | 276 | 22 | 254 | 22
28 | 2009-07-10 | Software Module 4 | 413 | 4 | 364 | 49
28 | 2009-07-10 | Software Module 5 | 189 | 15 | 164 | 25
29 | 2009-07-17 | Software Module 1 | 223 | 9 | 199 | 24
29 | 2009-07-17 | Software Module 2 | 172 | 2 | 151 | 21
29 | 2009-07-17 | Software Module 3 | 321 | 13 | 296 | 25
29 | 2009-07-17 | Software Module 4 | 473 | 0 | 421 | 52
29 | 2009-07-17 | Software Module 5 | 223 | 22 | 192 | 31
30 | 2009-07-24 | Software Module 1 | 259 | 26 | 226 | 33
30 | 2009-07-24 | Software Module 2 | 195 | 0 | 172 | 23
30 | 2009-07-24 | Software Module 3 | 378 | 30 | 347 | 31
30 | 2009-07-24 | Software Module 4 | 548 | 22 | 476 | 72
30 | 2009-07-24 | Software Module 5 | 252 | 0 | 215 | 37
31 | 2009-07-31 | Software Module 1 | 287 | 6 | 252 | 35
31 | 2009-07-31 | Software Module 2 | 216 | 13 | 190 | 26
31 | 2009-07-31 | Software Module 3 | 427 | 38 | 394 | 33
31 | 2009-07-31 | Software Module 4 | 601 | 36 | 526 | 75
31 | 2009-07-31 | Software Module 5 | 280 | 3 | 238 | 42
32 | 2009-08-07 | Software Module 1 | 324 | 10 | 286 | 38
32 | 2009-08-07 | Software Module 2 | 239 | 24 | 210 | 29
32 | 2009-08-07 | Software Module 3 | 469 | 23 | 434 | 35
32 | 2009-08-07 | Software Module 4 | 656 | 7 | 577 | 79
32 | 2009-08-07 | Software Module 5 | 314 | 31 | 265 | 49
33 | 2009-08-14 | Software Module 1 | 363 | 25 | 323 | 40
33 | 2009-08-14 | Software Module 2 | 268 | 11 | 238 | 30
33 | 2009-08-14 | Software Module 3 | 517 | 31 | 478 | 39
33 | 2009-08-14 | Software Module 4 | 725 | 36 | 630 | 95
33 | 2009-08-14 | Software Module 5 | 343 | 24 | 289 | 54
34 | 2009-08-21 | Software Module 1 | 400 | 0 | 356 | 44
34 | 2009-08-21 | Software Module 2 | 294 | 0 | 263 | 31
34 | 2009-08-21 | Software Module 3 | 600 | 0 | 557 | 43
34 | 2009-08-21 | Software Module 4 | 798 | 0 | 694 | 104
34 | 2009-08-21 | Software Module 5 | 400 | 0 | 338 | 62

## Data CRs
Data Change Requests
Dates of change request status
CR # | Change Request | Department | New (entered) | Approved (in implementation) | Included (delivered) | Future CRs | Rejected or cancelled
1 | Change Request 001 | Department 5 | 2009-02-05 | 2009-02-09 | 2009-03-05
2 | Change Request 002 | Department 1 | 2009-02-13 | 2009-02-18 | 2009-03-06
3 | Change Request 003 | Department 1 | 2009-02-19 | 2009-03-23 | 2009-04-10
4 | Change Request 004 | Department 2 | 2009-03-02 | 2009-03-05 | 2009-03-16
5 | Change Request 005 | Department 1 | 2009-03-06 |  |  | 2009-03-11
6 | Change Request 006 | IT | 2009-03-16 | 2009-03-20 | 2009-04-08
7 | Change Request 007 | IT | 2009-03-17 | 2009-03-20 | 2009-04-06
8 | Change Request 008 | IT | 2009-03-25 |  |  | 2009-03-30
9 | Change Request 009 | Department 3 | 2009-03-31 | 2009-04-02 | 2009-04-13
10 | Change Request 010 | Department 2 | 2009-04-08 | 2009-04-13 | 2009-04-28
11 | Change Request 011 | Department 2 | 2009-04-16 | 2009-04-17 | 2009-04-27
12 | Change Request 012 | Department 5 | 2009-04-17 | 2009-04-21 | 2009-05-08
13 | Change Request 013 | Department 1 | 2009-04-16 | 2009-04-20 | 2009-05-14
14 | Change Request 014 | Department 2 | 2009-04-20 |  |  |  | 2009-04-22
15 | Change Request 015 | Department 2 | 2009-04-24 | 2009-04-27 | 2009-05-12
16 | Change Request 016 | Department 4 | 2009-05-01 |  |  |  | 2009-05-06
17 | Change Request 017 | Department 3 | 2009-05-01 | 2009-05-05 | 2009-05-21
18 | Change Request 018 | Department 4 | 2009-05-04 | 2009-05-07 | 2009-05-25
19 | Change Request 019 | Department 1 | 2009-05-05 | 2009-05-07 | 2009-05-15
20 | Change Request 020 | Department 3 | 2009-05-05 | 2009-05-08 | 2009-05-19
21 | Change Request 021 | Department 4 | 2009-05-18 | 2009-05-25 | 2009-06-09
22 | Change Request 022 | Department 4 | 2009-05-20 |  |  | 2009-05-25
23 | Change Request 023 | IT | 2009-05-21 | 2009-05-26 | 2009-06-02
24 | Change Request 024 | Department 5 | 2009-05-29 | 2009-06-03 | 2009-06-16
25 | Change Request 025 | Department 2 | 2009-06-05 |  |  |  | 2009-06-10
26 | Change Request 026 | Department 4 | 2009-06-11 | 2009-06-15 | 2009-07-09
27 | Change Request 027 | Department 3 | 2009-06-18 |  |  | 2009-06-22
28 | Change Request 028 | Department 2 | 2009-06-18 | 2009-06-22 | 2009-07-13
29 | Change Request 029 | IT | 2009-06-22 | 2009-06-25 | 2009-07-08
30 | Change Request 030 | Department 3 | 2009-06-26 |  |  |  | 2009-07-01
31 | Change Request 031 | Department 3 | 2009-06-26 |  |  |  | 2009-06-29
32 | Change Request 032 | Department 2 | 2009-07-02 | 2009-07-06 | 2009-07-28
33 | Change Request 033 | Department 2 | 2009-07-07 | 2009-07-10 | 2009-07-22
34 | Change Request 034 | Department 2 | 2009-07-15 | 2009-07-20 | 2009-07-29
35 | Change Request 035 | IT | 2009-07-24 |  |  | 2009-07-27
36 | Change Request 036 | Department 1 | 2009-07-24 | 2009-07-28 | 2009-08-12
37 | Change Request 037 | Department 1 | 2009-07-28 | 2009-07-31 | 2009-08-17
38 | Change Request 038 | Department 2 | 2009-07-29 | 2009-08-03 | 2009-08-20
39 | Change Request 039 | Department 1 | 2009-08-14 |  |  |  | 2009-08-19
40 | Change Request 040 | Department 1 | 2009-08-24 | 2009-08-27
41 | Change Request 041 | Department 3 | 2009-09-01 |  |  |  | 2009-09-04
42 | Change Request 042 | Department 1 | 2009-09-03 | 2009-09-04
43 | Change Request 043 | Department 4 | 2009-09-09 |  |  |  | 2009-09-14
44 | Change Request 044 | Department 1 | 2009-09-11 |  |  |  | 2009-09-14
45 | Change Request 045 | Department 3 | 2009-09-21 | 2009-09-24
46 | Change Request 046 | Department 4 | 2009-09-22 |  |  |  | 2009-09-28
47 | Change Request 047 | Department 1 | 2009-09-24 | 2009-09-29
48 | Change Request 048 | Department 1 | 2009-09-24 | 2009-09-29
49 | Change Request 049 | Department 2 | 2009-09-25 | 2009-09-28
50 | Change Request 050 | Department 1 | 2009-09-30 |  |  |  | 2009-10-02

## Control Defects
Defects - Control
| Cosmetical | Minor | Major | Critical | Total
assigned | 3 | 14 | 23 | 3 | 43
resolved | 0 | 7 | 9 | 0 | 16
closed | 9 | 79 | 92 | 16 | 196
Total | 12 | 100 | 124 | 19 | 255
Week | Start | End | Assigned | Resolved | Closed | Assigned cumulated | Resolved cumulated | Closed cumulated | Assigned to resolved | Resolved to closed | Assigned to closed | Assigned to resolved | Resolved to closed | Assigned to closed
11 | 2009-03-09 | 2009-03-15 | 19 | 13 | 5 | 86 | 43 | 27 | 9.7442 | 3 | 11.8519 | 9.7442 | 3 | 11.8519
12 | 2009-03-16 | 2009-03-22 | 5 | 10 | 3 | 91 | 53 | 30 | 10.3208 | 2.9667 | 12.1667 | 10.3208 | 2.9667 | 12.1667
13 | 2009-03-23 | 2009-03-29 | 11 | 2 | 11 | 102 | 55 | 41 | 10.6182 | 5.9268 | 15.0976 | 10.6182 | 5.9268 | 15.0976
14 | 2009-03-30 | 2009-04-05 | 5 | 16 | 7 | 107 | 71 | 48 | 11.9859 | 6.75 | 16.8958 | 11.9859 | 6.75 | 16.8958
15 | 2009-04-06 | 2009-04-12 | 13 | 25 | 13 | 120 | 96 | 61 | 16.3958 | 6.2787 | 19.377 | 16.3958 | 6.2787 | 19.377
16 | 2009-04-13 | 2009-04-19 | 13 | 12 | 11 | 133 | 108 | 72 | 16.6111 | 6.9028 | 21.6806 | 16.6111 | 6.9028 | 21.6806
17 | 2009-04-20 | 2009-04-26 | 8 | 4 | 14 | 141 | 112 | 86 | 17 | 7.5233 | 22.4302 | 17 | 7.5233 | 22.4302
18 | 2009-04-27 | 2009-05-03 | 17 | 6 | 9 | 158 | 118 | 95 | 16.7119 | 8.3368 | 23.7684 | 16.7119 | 8.3368 | 23.7684
19 | 2009-05-04 | 2009-05-10 | 12 | 7 | 13 | 170 | 125 | 108 | 16.568 | 9.7685 | 25.6759 | 16.568 | 9.7685 | 25.6759
20 | 2009-05-11 | 2009-05-17 | 5 | 7 | 3 | 175 | 132 | 111 | 16.6439 | 9.6036 | 25.6667 | 16.6439 | 9.6036 | 25.6667
21 | 2009-05-18 | 2009-05-24 | 10 | 20 | 14 | 185 | 152 | 125 | 17.6447 | 8.968 | 25.8 | 17.6447 | 8.968 | 25.8
22 | 2009-05-25 | 2009-05-31 | 14 | 14 | 11 | 199 | 166 | 136 | 17.3976 | 8.5956 | 25.6838 | 17.3976 | 8.5956 | 25.6838
23 | 2009-06-01 | 2009-06-07 | 17 | 9 | 12 | 216 | 175 | 148 | 16.96 | 8.5946 | 25.3243 | 16.96 | 8.5946 | 25.3243
24 | 2009-06-08 | 2009-06-14 | 10 | 11 | 26 | 226 | 186 | 174 | 16.4839 | 11.5115 | 28.3506 | 16.4839 | 11.5115 | 28.3506
25 | 2009-06-15 | 2009-06-21 | 1 | 1 | 0 | 227 | 187 | 174 | 16.4385 | 11.5115 | 28.3506 | 16.4385 | 11.5115 | 28.3506
26 | 2009-06-22 | 2009-06-28 | 9 | 3 | 0 | 236 | 190 | 174 | 16.4421 | 11.5115 | 28.3506 | 16.4421 | 11.5115 | 28.3506
27 | 2009-06-29 | 2009-07-05 | 9 | 13 | 11 | 245 | 203 | 185 | 16.5369 | 11.6703 | 28.4919 | 16.5369 | 11.6703 | 28.4919
28 | 2009-07-06 | 2009-07-12 | 10 | 9 | 11 | 255 | 212 | 196 | 17.9434 | 12.6684 | 29.5561 | 17.9434 | 12.6684 | 29.5561
| Cosmetical | Minor | Major | Critical | Total
Assigned to resolved | 10.7778 | 20.8721 | 17.5446 | 8.75 | 17.9434
Resolved to closed | 6.6667 | 13.9241 | 13.2826 | 6.3125 | 12.6684
Assigned to closed | 17.4444 | 31.7215 | 31.4022 | 15.0625 | 29.5561
Week ISO 8601 | Start | End
2 | 2009-01-05 | 2009-01-11
3 | 2009-01-12 | 2009-01-18
4 | 2009-01-19 | 2009-01-25
5 | 2009-01-26 | 2009-02-01
6 | 2009-02-02 | 2009-02-08
7 | 2009-02-09 | 2009-02-15
8 | 2009-02-16 | 2009-02-22
9 | 2009-02-23 | 2009-03-01
10 | 2009-03-02 | 2009-03-08
11 | 2009-03-09 | 2009-03-15
12 | 2009-03-16 | 2009-03-22
13 | 2009-03-23 | 2009-03-29
14 | 2009-03-30 | 2009-04-05
15 | 2009-04-06 | 2009-04-12
16 | 2009-04-13 | 2009-04-19
17 | 2009-04-20 | 2009-04-26
18 | 2009-04-27 | 2009-05-03
19 | 2009-05-04 | 2009-05-10
20 | 2009-05-11 | 2009-05-17
21 | 2009-05-18 | 2009-05-24
22 | 2009-05-25 | 2009-05-31
23 | 2009-06-01 | 2009-06-07
24 | 2009-06-08 | 2009-06-14
25 | 2009-06-15 | 2009-06-21
26 | 2009-06-22 | 2009-06-28
27 | 2009-06-29 | 2009-07-05
28 | 2009-07-06 | 2009-07-12
29 | 2009-07-13 | 2009-07-19
30 | 2009-07-20 | 2009-07-26
31 | 2009-07-27 | 2009-08-02
32 | 2009-08-03 | 2009-08-09
33 | 2009-08-10 | 2009-08-16
34 | 2009-08-17 | 2009-08-23
35 | 2009-08-24 | 2009-08-30
36 | 2009-08-31 | 2009-09-06
37 | 2009-09-07 | 2009-09-13
38 | 2009-09-14 | 2009-09-20
39 | 2009-09-21 | 2009-09-27
40 | 2009-09-28 | 2009-10-04
41 | 2009-10-05 | 2009-10-11
42 | 2009-10-12 | 2009-10-18
43 | 2009-10-19 | 2009-10-25
44 | 2009-10-26 | 2009-11-01
45 | 2009-11-02 | 2009-11-08
46 | 2009-11-09 | 2009-11-15
47 | 2009-11-16 | 2009-11-22
48 | 2009-11-23 | 2009-11-29
49 | 2009-11-30 | 2009-12-06
50 | 2009-12-07 | 2009-12-13
51 | 2009-12-14 | 2009-12-20
52 | 2009-12-21 | 2009-12-27
53 | 2009-12-28 | 2010-01-03
Formulas:
Cosmetical = [Minor]-6
Cosmetical = [Cosmetical, row above]+7
Minor = [Minor, row below]-7
Minor = [Cosmetical]+6

## Control Test
Test - Control
Calculations / Consolidation
Software Module 1
Day | Week | # TCs planned total | # TCs planned actual | #TCs finished | #TCs not completed | #TCs passed | #TCs failed | Success rate | Completion rate | Actual in % of plan
2009-06-05 | 23 | 400 | 34 | 29 | 1 | 25 | 4 | 86.21% | 7.25% | 85.29%
2009-06-12 | 24 | 400 | 68 | 67 | 5 | 60 | 7 | 89.55% | 16.75% | 98.53%
2009-06-19 | 25 | 400 | 102 | 102 | 0 | 93 | 9 | 91.18% | 25.5% | 100%
2009-06-26 | 26 | 400 | 136 | 131 | 12 | 117 | 14 | 89.31% | 32.75% | 96.32%
2009-07-03 | 27 | 400 | 170 | 158 | 3 | 139 | 19 | 87.97% | 39.5% | 92.94%
2009-07-10 | 28 | 400 | 204 | 192 | 17 | 170 | 22 | 88.54% | 48% | 94.12%
2009-07-17 | 29 | 400 | 238 | 223 | 9 | 199 | 24 | 89.24% | 55.75% | 93.7%
2009-07-24 | 30 | 400 | 272 | 259 | 26 | 226 | 33 | 87.26% | 64.75% | 95.22%
2009-07-31 | 31 | 400 | 306 | 287 | 6 | 252 | 35 | 87.8% | 71.75% | 93.79%
2009-08-07 | 32 | 400 | 340 | 324 | 10 | 286 | 38 | 88.27% | 81% | 95.29%
2009-08-14 | 33 | 400 | 374 | 363 | 25 | 323 | 40 | 88.98% | 90.75% | 97.06%
2009-08-21 | 34 | 400 | 400 | 400 | 0 | 356 | 44 | 89% | 100% | 100%
Software Module 2
Day | Week | # TCs planned total | # TCs planned actual | #TCs finished | #TCs not completed | #TCs passed | #TCs failed | Success rate | Completion rate | Actual in % of plan
2009-06-05 | 23 | 300 | 25 | 21 | 1 | 19 | 2 | 90.48% | 7% | 84%
2009-06-12 | 24 | 300 | 50 | 51 | 2 | 46 | 5 | 90.2% | 17% | 102%
2009-06-19 | 25 | 300 | 75 | 71 | 4 | 62 | 9 | 87.32% | 23.67% | 94.67%
2009-06-26 | 26 | 300 | 100 | 92 | 6 | 80 | 12 | 86.96% | 30.67% | 92%
2009-07-03 | 27 | 300 | 125 | 116 | 0 | 102 | 14 | 87.93% | 38.67% | 92.8%
2009-07-10 | 28 | 300 | 150 | 144 | 9 | 126 | 18 | 87.5% | 48% | 96%
2009-07-17 | 29 | 300 | 175 | 172 | 2 | 151 | 21 | 87.79% | 57.33% | 98.29%
2009-07-24 | 30 | 300 | 200 | 195 | 0 | 172 | 23 | 88.21% | 65% | 97.5%
2009-07-31 | 31 | 300 | 225 | 216 | 13 | 190 | 26 | 87.96% | 72% | 96%
2009-08-07 | 32 | 300 | 250 | 239 | 24 | 210 | 29 | 87.87% | 79.67% | 95.6%
2009-08-14 | 33 | 300 | 275 | 268 | 11 | 238 | 30 | 88.81% | 89.33% | 97.45%
2009-08-21 | 34 | 300 | 300 | 294 | 0 | 263 | 31 | 89.46% | 98% | 98%
Software Module 3
Day | Week | # TCs planned total | # TCs planned actual | #TCs finished | #TCs not completed | #TCs passed | #TCs failed | Success rate | Completion rate | Actual in % of plan
2009-06-05 | 23 | 600 | 50 | 49 | 1 | 46 | 3 | 93.88% | 8.167% | 98%
2009-06-12 | 24 | 600 | 100 | 97 | 9 | 92 | 5 | 94.85% | 16.17% | 97%
2009-06-19 | 25 | 600 | 150 | 143 | 13 | 129 | 14 | 90.21% | 23.83% | 95.33%
2009-06-26 | 26 | 600 | 200 | 189 | 0 | 173 | 16 | 91.53% | 31.5% | 94.5%
2009-07-03 | 27 | 600 | 250 | 229 | 0 | 212 | 17 | 92.58% | 38.17% | 91.6%
2009-07-10 | 28 | 600 | 300 | 276 | 22 | 254 | 22 | 92.03% | 46% | 92%
2009-07-17 | 29 | 600 | 350 | 321 | 13 | 296 | 25 | 92.21% | 53.5% | 91.71%
2009-07-24 | 30 | 600 | 400 | 378 | 30 | 347 | 31 | 91.8% | 63% | 94.5%
2009-07-31 | 31 | 600 | 450 | 427 | 38 | 394 | 33 | 92.27% | 71.17% | 94.89%
2009-08-07 | 32 | 600 | 500 | 469 | 23 | 434 | 35 | 92.54% | 78.17% | 93.8%
2009-08-14 | 33 | 600 | 550 | 517 | 31 | 478 | 39 | 92.46% | 86.17% | 94%
2009-08-21 | 34 | 600 | 600 | 600 | 0 | 557 | 43 | 92.83% | 100% | 100%
Software Module 4
Day | Week | # TCs planned total | # TCs planned actual | #TCs finished | #TCs not completed | #TCs passed | #TCs failed | Success rate | Completion rate | Actual in % of plan
2009-06-05 | 23 | 800 | 67 | 55 | 2 | 49 | 6 | 89.09% | 6.875% | 82.09%
2009-06-12 | 24 | 800 | 134 | 132 | 7 | 120 | 12 | 90.91% | 16.5% | 98.51%
2009-06-19 | 25 | 800 | 201 | 210 | 11 | 180 | 30 | 85.71% | 26.25% | 104.5%
2009-06-26 | 26 | 800 | 268 | 271 | 24 | 236 | 35 | 87.08% | 33.88% | 101.1%
2009-07-03 | 27 | 800 | 335 | 342 | 24 | 307 | 35 | 89.77% | 42.75% | 102.1%
2009-07-10 | 28 | 800 | 402 | 413 | 4 | 364 | 49 | 88.14% | 51.62% | 102.7%
2009-07-17 | 29 | 800 | 469 | 473 | 0 | 421 | 52 | 89.01% | 59.13% | 100.9%
2009-07-24 | 30 | 800 | 536 | 548 | 22 | 476 | 72 | 86.86% | 68.5% | 102.2%
2009-07-31 | 31 | 800 | 603 | 601 | 36 | 526 | 75 | 87.52% | 75.12% | 99.67%
2009-08-07 | 32 | 800 | 670 | 656 | 7 | 577 | 79 | 87.96% | 82% | 97.91%
2009-08-14 | 33 | 800 | 737 | 725 | 36 | 630 | 95 | 86.9% | 90.62% | 98.37%
2009-08-21 | 34 | 800 | 800 | 798 | 0 | 694 | 104 | 86.97% | 99.75% | 99.75%
Software Module 5
Day | Week | # TCs planned total | # TCs planned actual | #TCs finished | #TCs not completed | #TCs passed | #TCs failed | Success rate | Completion rate | Actual in % of plan
2009-06-05 | 23 | 400 | 34 | 37 | 2 | 30 | 7 | 81.08% | 9.25% | 108.8%
2009-06-12 | 24 | 400 | 68 | 68 | 1 | 59 | 9 | 86.76% | 17% | 100%
2009-06-19 | 25 | 400 | 102 | 98 | 0 | 86 | 12 | 87.76% | 24.5% | 96.08%
2009-06-26 | 26 | 400 | 136 | 125 | 4 | 104 | 21 | 83.2% | 31.25% | 91.91%
2009-07-03 | 27 | 400 | 170 | 156 | 8 | 133 | 23 | 85.26% | 39% | 91.76%
2009-07-10 | 28 | 400 | 204 | 189 | 15 | 164 | 25 | 86.77% | 47.25% | 92.65%
2009-07-17 | 29 | 400 | 238 | 223 | 22 | 192 | 31 | 86.1% | 55.75% | 93.7%
2009-07-24 | 30 | 400 | 272 | 252 | 0 | 215 | 37 | 85.32% | 63% | 92.65%
2009-07-31 | 31 | 400 | 306 | 280 | 3 | 238 | 42 | 85% | 70% | 91.5%
2009-08-07 | 32 | 400 | 340 | 314 | 31 | 265 | 49 | 84.39% | 78.5% | 92.35%
2009-08-14 | 33 | 400 | 374 | 343 | 24 | 289 | 54 | 84.26% | 85.75% | 91.71%
2009-08-21 | 34 | 400 | 400 | 400 | 0 | 338 | 62 | 84.5% | 100% | 100%
Total
Day | Week | # TCs planned total | # TCs planned actual | #TCs finished | #TCs not completed | #TCs passed | #TCs failed | Success rate | Completion rate | Actual in % of plan
2009-06-05 | 23 | 2500 | 210 | 191 | 7 | 169 | 22 | 88.48% | 7.64% | 90.95%
2009-06-12 | 24 | 2500 | 420 | 415 | 24 | 377 | 38 | 90.84% | 16.6% | 98.81%
2009-06-19 | 25 | 2500 | 630 | 624 | 28 | 550 | 74 | 88.14% | 24.96% | 99.05%
2009-06-26 | 26 | 2500 | 840 | 808 | 46 | 710 | 98 | 87.87% | 32.32% | 96.19%
2009-07-03 | 27 | 2500 | 1050 | 1001 | 35 | 893 | 108 | 89.21% | 40.04% | 95.33%
2009-07-10 | 28 | 2500 | 1260 | 1214 | 67 | 1078 | 136 | 88.8% | 48.56% | 96.35%
2009-07-17 | 29 | 2500 | 1470 | 1412 | 46 | 1259 | 153 | 89.16% | 56.48% | 96.05%
2009-07-24 | 30 | 2500 | 1680 | 1632 | 78 | 1436 | 196 | 87.99% | 65.28% | 97.14%
2009-07-31 | 31 | 2500 | 1890 | 1811 | 96 | 1600 | 211 | 88.35% | 72.44% | 95.82%
2009-08-07 | 32 | 2500 | 2100 | 2002 | 95 | 1772 | 230 | 88.51% | 80.08% | 95.33%
2009-08-14 | 33 | 2500 | 2310 | 2216 | 127 | 1958 | 258 | 88.36% | 88.64% | 95.93%
2009-08-21 | 34 | 2500 | 2500 | 2492 | 0 | 2208 | 284 | 88.6% | 99.68% | 99.68%
Dashboard Table
| # TCs planned total | # TCs planned actual | # TCs executed |  |  |  |  | Success rate in % | Completion rate | Actual in % of plan
|  |  | started | not yet finished | finished | thereof passed | thereof failed
Software Module 1 | 400 | 204 | 209 | 17 | 192 | 170 | 22 | 88.54% | 48% | 94.12%
Software Module 2 | 300 | 150 | 153 | 9 | 144 | 126 | 18 | 87.5% | 48% | 96%
Software Module 3 | 600 | 300 | 298 | 22 | 276 | 254 | 22 | 92.03% | 46% | 92%
Software Module 4 | 800 | 402 | 417 | 4 | 413 | 364 | 49 | 88.14% | 51.62% | 102.7%
Software Module 5 | 400 | 204 | 204 | 15 | 189 | 164 | 25 | 86.77% | 47.25% | 92.65%
Total | 2500 | 1260 | 1281 | 67 | 1214 | 1078 | 136 | 88.8% | 48.56% | 96.35%
Bar Chart Success Rate
| Bar Value | Bar Dummy | Target X | Scale Dummy | Y
Software Module 1 | 88.54% |  | 87% | 100% | 0%
Software Module 2 | 87.5% |  | 87% | 100% | 0%
Software Module 3 | 92.03% |  | 87% | 100% | 0%
Software Module 4 | 88.14% |  | 87% | 100% | 0%
Software Module 5 | 86.77% |  | 87% | 100% | 0%
Total | 88.8% | 100% | 87% | 100% | 100%
Bar Chart Completion Rate
| Bar Value | Bar Dummy | Target X | Scale Dummy | Y
Software Module 1 | 94.12% |  | 100% | 102.7% | 0%
Software Module 2 | 96% |  | 100% | 102.7% | 0%
Software Module 3 | 92% |  | 100% | 102.7% | 0%
Software Module 4 | 102.7% |  | 100% | 102.7% | 0%
Software Module 5 | 92.65% |  | 100% | 102.7% | 0%
Total | 96.35% | 102.7% | 100% | 102.7% | 100%
Column Chart Actual vs Plan
Week | # TCs planned | #TCs finished | Scale Dummy
23 | 210 | 191
24 | 420 | 415
25 | 630 | 624
26 | 840 | 808
27 | 1050 | 1001
28 | 1260 | 1214
29 | 0 | 0
30 | 0 | 0
31 | 0 | 0
32 | 0 | 0
33 | 0 | 0
34 | 0 | 0 | 1260
Column Chart Success Rate
Week | #TCs passed | Threshold X | Success rate threshold | Scale Dummy
23 | 169 | 1 | 183
24 | 377 | 2 | 365
25 | 550 | 3 | 548
26 | 710 | 4 | 731
27 | 893 | 5 | 914
28 | 1078 | 6 | 1096
29 | 0 | 7 | 1279
30 | 0 | 8 | 1462
31 | 0 | 9 | 1644
32 | 0 | 10 | 1827
33 | 0 | 11 | 2010
34 | 0 | 12 | 2175 | 2175

## Control CRs
Change Requests - Control
Calculations / Consolidation
|  | CRs by status | [5 empty] | CRs by departments (cumulated)
Friday of week | Week | Total cumulated | In investigation | Approved (in implementation) cumulated | Included (delivered) cumulated | Future CRs | Rejected or cancelled | Department 1 | Department 2 | Department 3 | Department 4 | Department 5 | IT
2009-01-09 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009-01-16 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009-01-23 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009-01-30 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009-02-06 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
2009-02-13 | 7 | 2 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
2009-02-20 | 8 | 3 | 1 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0
2009-02-27 | 9 | 3 | 1 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0
2009-03-06 | 10 | 5 | 2 | 3 | 2 | 0 | 0 | 3 | 1 | 0 | 0 | 1 | 0
2009-03-13 | 11 | 5 | 1 | 3 | 2 | 1 | 0 | 3 | 1 | 0 | 0 | 1 | 0
2009-03-20 | 12 | 7 | 1 | 5 | 3 | 1 | 0 | 3 | 1 | 0 | 0 | 1 | 2
2009-03-27 | 13 | 8 | 1 | 6 | 3 | 1 | 0 | 3 | 1 | 0 | 0 | 1 | 3
2009-04-03 | 14 | 9 | 0 | 7 | 3 | 2 | 0 | 3 | 1 | 1 | 0 | 1 | 3
2009-04-10 | 15 | 10 | 1 | 7 | 6 | 2 | 0 | 3 | 2 | 1 | 0 | 1 | 3
2009-04-17 | 16 | 13 | 2 | 9 | 7 | 2 | 0 | 4 | 3 | 1 | 0 | 2 | 3
2009-04-24 | 17 | 15 | 1 | 11 | 7 | 2 | 1 | 4 | 5 | 1 | 0 | 2 | 3
2009-05-01 | 18 | 17 | 2 | 12 | 9 | 2 | 1 | 4 | 5 | 2 | 1 | 2 | 3
2009-05-08 | 19 | 20 | 0 | 16 | 10 | 2 | 2 | 5 | 5 | 3 | 2 | 2 | 3
2009-05-15 | 20 | 20 | 0 | 16 | 13 | 2 | 2 | 5 | 5 | 3 | 2 | 2 | 3
2009-05-22 | 21 | 23 | 3 | 16 | 15 | 2 | 2 | 5 | 5 | 3 | 4 | 2 | 4
2009-05-29 | 22 | 24 | 1 | 18 | 16 | 3 | 2 | 5 | 5 | 3 | 4 | 3 | 4
2009-06-05 | 23 | 25 | 1 | 19 | 17 | 3 | 2 | 5 | 6 | 3 | 4 | 3 | 4
2009-06-12 | 24 | 26 | 1 | 19 | 18 | 3 | 3 | 5 | 6 | 3 | 5 | 3 | 4
2009-06-19 | 25 | 28 | 2 | 20 | 19 | 3 | 3 | 5 | 7 | 4 | 5 | 3 | 4
2009-06-26 | 26 | 31 | 2 | 22 | 19 | 4 | 3 | 5 | 7 | 6 | 5 | 3 | 5
2009-07-03 | 27 | 32 | 1 | 22 | 19 | 4 | 5 | 5 | 8 | 6 | 5 | 3 | 5
2009-07-10 | 28 | 33 | 0 | 24 | 21 | 4 | 5 | 5 | 9 | 6 | 5 | 3 | 5
2009-07-17 | 29 | 34 | 1 | 24 | 22 | 4 | 5 | 5 | 10 | 6 | 5 | 3 | 5
2009-07-24 | 30 | 36 | 2 | 25 | 23 | 4 | 5 | 6 | 10 | 6 | 5 | 3 | 6
2009-07-31 | 31 | 38 | 1 | 27 | 25 | 5 | 5 | 7 | 11 | 6 | 5 | 3 | 6
2009-08-07 | 32 | 38 | 0 | 28 | 25 | 5 | 5 | 7 | 11 | 6 | 5 | 3 | 6
2009-08-14 | 33 | 39 | 1 | 28 | 26 | 5 | 5 | 8 | 11 | 6 | 5 | 3 | 6
2009-08-21 | 34 | 39 | 0 | 28 | 28 | 5 | 6 | 8 | 11 | 6 | 5 | 3 | 6
2009-08-28 | 35 | 40 | 0 | 29 | 28 | 5 | 6 | 9 | 11 | 6 | 5 | 3 | 6
2009-09-04 | 36 | 42 | 0 | 30 | 28 | 5 | 7 | 10 | 11 | 7 | 5 | 3 | 6
2009-09-11 | 37 | 44 | 2 | 30 | 28 | 5 | 7 | 11 | 11 | 7 | 6 | 3 | 6
2009-09-18 | 38 | 44 | 0 | 30 | 28 | 5 | 9 | 11 | 11 | 7 | 6 | 3 | 6
2009-09-25 | 39 | 49 | 4 | 31 | 28 | 5 | 9 | 13 | 12 | 8 | 7 | 3 | 6
2009-10-02 | 40 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
2009-10-09 | 41 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
2009-10-16 | 42 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
2009-10-23 | 43 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
2009-10-30 | 44 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
2009-11-06 | 45 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
2009-11-13 | 46 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
2009-11-20 | 47 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
2009-11-27 | 48 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
2009-12-04 | 49 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
2009-12-11 | 50 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
2009-12-18 | 51 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
2009-12-25 | 52 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
2010-01-01 | 53 | 50 | 0 | 34 | 28 | 5 | 11 | 14 | 12 | 8 | 7 | 3 | 6
Overview KPI
Total CRs last week |  | 32
New this week |  | 1
Total CRs this week |  | 33
thereof business |  | 28 | 84.85%
thereof IT |  | 5 | 15.15%
Waterfall Chart
| Total | In investigation | Approved (in implementation) | Included (delivered) | Future CRs | Rejected or cancelled
Actuals | 33 | 0 | 3 | 21 | 4 | 5
Invisible | 0 | 0 | 0 | 3 | 24 | 28
Sorted Bar Chart
Department | CRs | No. | Dummy Value | Position | Departments sorted | Value
Department 1 | 5 | 1 | 5 | 5 | Department 5 | 3
Department 2 | 9 | 2 | 9 | 1 | Department 1 | 5
Department 3 | 6 | 3 | 6 | 4 | Department 4 | 5
Department 4 | 5 | 4 | 5 | 6 | IT | 5
Department 5 | 3 | 5 | 3 | 3 | Department 3 | 6
IT | 5 | 6 | 5 | 2 | Department 2 | 9
Formulas:
Friday of week = [Friday of week, row above]+7

## Control General
Control General
Selected Week # | 27
Last Date | 2009-11-26
Last Sunday | 2009-11-29
Latest week
Monday selected week | 2009-07-06
Friday selected week | 2009-07-10
Sunday selected week | 2009-07-12
Selected week | 28
Test Dashboard Control
Start Week | 22
Week Control | 6
# of weeks | 12
Display Data on Test | TRUE
Scale Factor PPT Export | 75%
List of PPT Titles
Software Defects
Testing
Change Requests