## Content
Content Calendar
[7 empty] | Display Start: | 2020-05-05 |  | 2020-05-04 | [6 empty] | 2020-05-11 | [6 empty] | 2020-05-18 | [6 empty] | 2020-05-25 | [6 empty] | 2020-06-01 | [6 empty] | 2020-06-08
[7 empty] | Start Week: | 1 | time axis 2020-05-04 to 2020-06-14
| STATUS | TITLE | PRIORITY | SHORT DESCRIPTION | DESC LENGTH | ASSIGNED TO | DRAFT DATE | PUBLISH DATE | LINK | time axis 2020-05-04 to 2020-06-14
-
| PLANNED | How to Learn to Fly | High | This is a short description of this content and the description wraps to 2 lines. | 81 | Tom | 2020-05-08 | 2020-05-15 | https://www.vertex42.com/calendars/content-calendar.html | bar: 2020-05-08; 2020-05-15
| ON HOLD | Awesome Travel Points | Medium |  | - | Angie | 2020-05-11 | 2020-05-18 | bar: 2020-05-11; 2020-05-18
| ASSIGNED | Top 10 Stock Picks | Medium |  | - | Sarah | 2020-05-13 | 2020-05-19 | bar: 2020-05-13; 2020-05-19
| IN PROGRESS | 10 Things to Avoid | High |  | - | Matt | 2020-05-15 | 2020-05-20 | bar: 2020-05-15; 2020-05-20
| READY | Top CMS Solutions | Low |  | - | Angie | 2020-05-08 | 2020-05-15 | bar: 2020-05-08; 2020-05-15
| PUBLISHED | Marketing 101 | Low |  | - | Matt | 2020-05-13 | 2020-05-18 | bar: 2020-05-13; 2020-05-18
| ON HOLD | How to Watch Paint Dry |  |  | - |  | 2020-05-12 | 2020-05-21 | bar: 2020-05-12; 2020-05-21
-
-
-
-
|  | Insert new rows ABOVE this one |  |  | -
😎 DONE
|  | Move rows here after they are published and you no longer need to see them in your list | [6 empty] | {42}

## Calendar
MAY 2020 | [7 empty] | Content Calendar
Date: | 2020-05-01
2020-05-03 |  | 2020-05-04 |  | 2020-05-05 |  | 2020-05-06 |  | 2020-05-07 |  | 2020-05-08 |  | 2020-05-09
2020-04-26 |  | 2020-04-27 |  | 2020-04-28 |  | 2020-04-29 |  | 2020-04-30 |  | 2020-05-01 |  | 2020-05-02
Lists only 3 items per day
2020-05-03 |  | 2020-05-04 | Star Wars Day | 2020-05-05 | Cinco de Mayo | 2020-05-06 |  | 2020-05-07 |  | 2020-05-08 |  | 2020-05-09 | Year:
2020
Month:
[13 empty] | May | 5
2020-05-10 | Mother's Day | 2020-05-11 |  | 2020-05-12 |  | 2020-05-13 |  | 2020-05-14 |  | 2020-05-15 |  | 2020-05-16 | Start Day:
[10 empty] | PLANNED | How to Learn to Fly |  | 1 | 1:Sun,2:Mon
[10 empty] | READY | Top CMS Solutions
Legend
2020-05-17 |  | 2020-05-18 | Victoria Day (Canada) | 2020-05-19 |  | 2020-05-20 |  | 2020-05-21 |  | 2020-05-22 |  | 2020-05-23 | PLANNED
|  | ON HOLD | Awesome Travel Points | ASSIGNED | Top 10 Stock Picks | IN PROGRESS | 10 Things to Avoid | ON HOLD | How to Watch Paint Dry |  |  |  | ON HOLD
|  | PUBLISHED | Marketing 101 | [9 empty] | ASSIGNED
IN PROGRESS
2020-05-24 |  | 2020-05-25 | Memorial Day | 2020-05-26 |  | 2020-05-27 |  | 2020-05-28 |  | 2020-05-29 |  | 2020-05-30 | READY
PUBLISHED
2020-05-31 |  | 2020-06-01 |  | 2020-06-02 |  | 2020-06-03 |  | 2020-06-04 |  | 2020-06-05 |  | 2020-06-06

## Hashtags
Hashtag Organizer
| Number Included: | 4
| First 4 Hashtags: | #spreadsheets #vertex42 #msexcel #learnexcel
HASHTAG | INCLUDE | SORT | TOPIC | IG POSTS | IG LINK | ◄ Use the Filter and Sort features
#spreadsheets | x | 1 | Spreadsheets | 26727 | View
#vertex42 | x | 2 | Spreadsheets | 60 | View
#msexcel | x | 3 | Spreadsheets | 12955 | View
#learnexcel | x | 5 | Spreadsheets | 1426 | View
#excelhelp |  | 4 | Spreadsheets | 527 | View
View
View
View
View
View
View
View
View
View
View
View
View
View
[5 empty] | View | ◄ To add more rows, drag the bottom right corner down.
Note on C6: INCLUDED: Place an "x" in this column so that you can either Sort or Filter your list using this column.
Note on D6: SORT: This column can help you modify the order of the hashtags in your list.
Note on E6: Topic: Categorize your hashtags so that you can sort and filter based on Topic.
Note on F6: IG Posts: Use this column to enter the number of posts on Instagram for each hashtag. This number is not automatically updated, but it's just for getting a general idea of the popularity of the hashtag, so the exact number may not be important.

## Settings
SETTINGS
Status Options
PLANNED |  | ◄ Change the labels as needed.
ON HOLD
ASSIGNED
IN PROGRESS
READY
PUBLISHED |  | ◄ Limit is 6 status options. To add more requires adding CF rules.
Priority Options
High |  | ◄ Conditional formatting controls the colors
Medium
Low
Assigned To Options
Tom
Sarah
Matt
Angie
◄ Insert new rows above this one if necessary
Weekends |  | 0000011
Highlight Weekends | yes
Monday | 0 | ◄ Enter "0" for a work day and "1" for a non-work day
Tuesday | 0
Wednesday | 0
Thursday | 0
Friday | 0
Saturday | 1
Sunday | 1
Year: | 2020
Holidays and Other Special Days to Mark on Calendar
Date |  | Reason
1899-12-31 |  | Do not delete this row
2022-04-15 |  | TODAY
2020-01-01 |  | New Years Day
2020-01-20 |  | ML King Day
2020-05-04 |  | Star Wars Day
2020-02-02 |  | Groundhog Day
2020-02-17 |  | Presidents' Day
2020-02-14 |  | Valentine's Day
2020-04-01 |  | April Fool's Day
2020-04-22 |  | Earth Day
2020-05-25 |  | Memorial Day
2020-05-05 |  | Cinco de Mayo
2020-05-10 |  | Mother's Day
2020-06-14 |  | Flag Day
2020-06-21 |  | Father's Day
2020-07-04 |  | Independence Day
2020-09-07 |  | Labor Day
2020-09-11 |  | Patriot Day
2020-09-17 |  | Constitution Day
2020-10-16 |  | Boss's Day
2020-10-24 |  | United Nations Day
2020-10-31 |  | Halloween
2020-11-11 |  | Veterans Day
2020-11-26 |  | Thanksgiving
2020-12-07 |  | Pearl Harbor
2020-12-24 |  | Christmas Eve
2020-12-25 |  | Christmas Day
2020-12-26 |  | Kwanzaa begins
2020-12-31 |  | New Year's Eve
2020-05-04 |  | May Day (UK)
2020-08-03 |  | Bank Holiday (UK)
2020-08-31 |  | Bank Holiday (UK)
2020-05-18 |  | Victoria Day (Canada)
2020-04-22 |  | Admin Assist Day
2020-04-12 |  | Easter
2020-01-25 |  | Chinese New Year
2020-04-24 |  | Ramadan begins
2020-09-19 |  | Rosh Hashanah
2020-12-10 |  | Hanukkah begins
2020-03-20 |  | Vernal equinox (GMT)
2020-06-20 |  | June Solstice (GMT)
2020-09-22 |  | Autumnal equinox (GMT)
2020-12-21 |  | Dec. Solstice (GMT)
◄ Insert new rows above this one if necessary
Note on A85: Custom formula © 2009 Vertex42 LLC Dates compared with table from timeanddate.com for 1900-2099. http://www.timeanddate.com/calendar/seasons.html
Note on A86: Custom formula © 2009 Vertex42 LLC Dates compared with table from timeanddate.com for 1900-2099. http://www.timeanddate.com/calendar/seasons.html
Note on A87: Custom formula © 2009 Vertex42 LLC Dates compared with table from timeanddate.com for 1900-2099. http://www.timeanddate.com/calendar/seasons.html
Note on A88: Custom formula © 2009 Vertex42 LLC Dates compared with table from timeanddate.com for 1900-2099. http://www.timeanddate.com/calendar/seasons.html

## Help
HELP
About This Template
This content calendar was designed to help plan and schedule content development for bloggers and other internet publishers. It can modified and used for other types of content development as well.
Instructions and Notes
Use the Settings Worksheet
You can change some of the labels and options in the Settings worksheet. You can also customize the list of holidays in the Settings worksheet.
Moving Rows
After you select an entire row (SHIFT+SPACE), if you hold the SHIFT key as you click and drag the edge of the selection with your mouse, you can use the mouse to drag the row to move it. This is a very convenient way to move rows.
Adding More Rows
When you insert new rows, you should insert a blank row between rows that have the formatting you want. If you do that, the formatting will be copied automatically.
IMPORTANT: After inserting a new row, copy a previous row and paste over the new row so that all of the formula are copied into the new row!
Changing the Colors
Changing the colors in the legends won't change anything. The best way to change the colors used for the 6 status options is to customize the Theme Colors (Accent colors 1-6). Go to Page Layout > Themes.
Conditional Formatting
This spreadsheet uses conditional formatting quite heavily. To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
Content Worksheet, Column B
Column B serves no functional purpose other than making the list look a bit more interesting, color-coded based on the Status.
Hashtags
The Hashtags worksheet provides a way to list your commonly used hashtags, using the Sort and Filter features in Excel to pick which of the hashtags you want to use in your post.