## Sheet1
Marketing Agency Gantt Chart
Start Date | 2021-03-01 |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
 | time axis 2021-03-01 to 2021-05-23
Task Description | Lead | Start Date | End Date | Progress | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Current Performance Analysis | Frank Mcgee | 2021-03-01 | 2021-03-14 | 80%
Review & Modify Objectives | Rick Waters | 2021-03-08 | 2021-03-21 | 75%
Requirements Analysis | Jerry Glover | 2021-03-21 | 2021-04-04 | 30%
Hiring Strategy | Taylor Pena | 2021-03-15 | 2021-03-28 | 60%
Develop & Communicate Plan of Action | Lowell Dixon | 2021-04-05 | 2021-04-25 | 50%
Implementation & Monitoring | Neal Snyder | 2021-04-26 | 2021-05-23 | 35%