## Recruiting Plan
"Company Name"
RECRUITING PLAN TEMPLATE
Recruiting Source | Budget | Hire Goal | Funded | Status | Assigned To | Comments | Start | Finish | Lessons Learned
2015 Recruiting Plan | 460400 | 155 | . |  |  |  | 2015-09-01 | 2016-12-30
Online Recruiting | 7800 | 30 | YES | In Progress | Alex Bright |  | 2016-01-01 | 2016-12-30
www.Monster.com | 1000 | 10 | YES | On Track |  | relationship established ready for postings | 2016-01-16 | 2016-09-06 | Great Hires!! Senior and Technical.
www.careerbuilder.com | 1000 | 10 | YES | On Track |  | relationship established ready for postings | 2016-01-01 | 2016-10-17 | Great place to get management candidates.
LinkedIn | 4800 | 5 | YES | On Track |  | all positions get posted here | 2016-04-04 | 2016-08-17
www.hotjobs.com | 1000 | 5 | YES | In Progress |  | not funded yet this calendar year, finding funding | 2016-01-01 | 2016-12-30
Vendor Agencies | 15600 | 60 | YES | In Progress | Jacob Senmark |  | 2015-09-14 | 2016-06-29
<<List agency 1>> | 25000 | 5 | YES | On Track |  |  | 2015-09-14 | 2016-02-12
<<List agency 2>> | 30000 | 8 | YES | At Risk |  | not funded yet this calendar year, finding funding | 2016-01-01 | 2016-06-29
<<List agency 3>> | 10000 | 3 | YES | On Track |  |  | 2016-03-01 | 2016-05-30 | Slow at delivering, look for new agency.
Campus Recruiting | 52000 | 13 | YES | In Progress | Anthony Gruenelli |  | 2015-09-01 | 2016-03-30
Targeted In-State Colleges | 7000 | 7 | YES | On Track | Sheila Erickson |  | 2015-09-01 | 2016-03-30
National Schools | 15000 | 3 | YES | In Progress | Derek Brown | potentially add one additional hi-pro shool | 2015-09-01 | 2016-03-30
International School | 30000 | 3 | YES | In Progress | Derek Brown | Working with Legal department to fix issues
Job Fairs | 10000 | 10 | YES |  | Anthony Gruenelli |  | 2016-01-10 | 2016-06-24
<<enter job fair location>> | 5000 | 5 | YES | In Progress |  | participating in June fair. finalizing contract | 2016-06-15 | 2016-06-24
<<enter job fair location>> | 5000 | 5 | YES | On Track |  | January event all lined up with participants | 2016-01-10 | 2016-01-22
University Partnerships | 5000 | 4 | YES |  | Anthony Gruenelli |  | 2015-09-01 | 2016-03-30
Central | 2500 | 2 | YES | Not Started | Sheila Erickson |  | 2015-09-01 | 2016-03-30
Eastern | 2500 | 2 | YES | On Track | Derek Brown |  | 2015-09-01 | 2016-03-30
Targeted Recruitment | 20000 | 7 | YES |  | Shari Wise |  | 2016-01-01 | 2016-12-30
Diversity Recruiting | 10000 | 5 | YES | On Track |  |  | 2016-01-01 | 2016-12-30
Executive Recruiting | 10000 | 2 | YES | On Track |  |  | 2016-01-01 | 2016-12-30
Internships | 325000 | 6 | YES |  | Kennedy Kerrigan |  | 2016-06-01 | 2016-08-30
10 Engineering Positions | 250000 | 5 | YES | In Progress | Sheila Erickson |  | 2016-06-01 | 2016-08-30
3 Marketing Positions | 75000 | 1 | YES | On Track | Derek Brown |  | 2016-06-01 | 2016-08-30
Recruiting Events | 15000 | 15 | YES |  | Frank Carlson |  | 2015-09-15 | 2016-05-04
Silicon Valley | 5000 | 5 | YES | On Track |  |  | 2015-09-15 | 2015-09-16
Seattle | 5000 | 5 | YES | On Track |  |  | 2016-02-22 | 2016-02-23
Vancouver | 5000 | 5 | YES | At Risk |  | not funded yet this calendar year, finding funding | 2016-05-03 | 2016-05-04
Employee Referrals | 10000 | 10 | YES | On Track | Kennedy Kerrigan |  | 2016-01-01 | 2016-12-30
Employee Referral Program | 10000 | 10 | YES | On Track |  |  | 2016-01-01 | 2016-12-30